## Sheet1
S.No | Progress | State | Date | Assignee | Time Taken | Sources
1 | Created Maven Project | Completed | 2023-04-13 | Sai Tej Sunkara | 20 Min | https://www.youtube.com/watch?v=bSaBmXFym30
2 | What is Traveling Salesman Problem | Yet to Start | 2023-04-13 | Sai Tej Sunkara | 1 Hour | https://www.youtube.com/watch?v=cY4HiiFHO1o
3 | What is actual solution for Traveling Salesman Problem | Yet to Start | 2023-04-13 | Sai Tej Sunkara | 1 Hour
4 | Actual Solution Implementation | Yet to Start | 2023-04-13 | Sai Tej Sunkara | 3 Hours
5 | What is Christofides Algorithm | Yet to Start | 2023-04-14 | Sai Tej Sunkara | 1 Hour
6 | Christofides Algorithm Implementation | Yet to Start | 2023-04-14 | Sai Tej Sunkara | 3 Hours
7 | Christofides Algorithm Unit Testing | Yet to Start | 2023-04-14 | Sai Tej Sunkara | 3 Hours
8 | GUI for Christofides Algorithm | Yet to Start | 2023-04-15 | Sai Tej Sunkara | 3 Hours
9 | Strategical Optimization 1 - Approach | Yet to Start | 2023-04-15 | Sai Tej Sunkara | 2 Hours
10 | Strategical Optimization 1 - Implementation | Yet to Start | 2023-04-15 | Sai Tej Sunkara | 3 Hours
11 | Strategical Optimization 2 - Approach | Yet to Start | 2023-04-16 | Sai Tej Sunkara | 2 Hours
12 | Strategical Optimization 2 - Implementation | Yet to Start | 2023-04-16 | Sai Tej Sunkara | 3 Hours
13 | Strategical Optimizations Unit Testing | Yet to Start | 2023-04-17 | Sai Tej Sunkara | 6 Hours
14 | Performance Analysis | Yet to Start | 2023-04-17 | Sai Tej Sunkara | 6 Hours